## README
RainReady (working name): Team Task Tracker
Sime Darby Property University Hackathon 2026 ¦ Planet: Climate resilience ¦ Site: Bandar Bukit Raja sub-catchment
Purpose
One place for every task, owner, hand-off, assumption and open item. Update the Status column on 'Task List'; the Summary and Timeline update automatically.
Settings (yellow cells are inputs)
| Day 1 date | 2026-10-10 | Change this if you start on another day. Timeline dates follow it.
| Submission deadline | 2026-10-23 | Proposal due 11:59 p.m. (from the competition briefing).
| Days remaining |  | Calculated.
| Project day today |  | Calculated. Day 1 = the Day 1 date above.
Team and leads (yellow = enter names)
| Role | Lead (name) | Focus
| Architecture |  | 3D modelling: site model, pond and wetland geometry, scenario visuals, web-ready 3D assets, visual style
| Mechanical |  | Analysis and hydrology: MSMA 2 inputs, storage required, pond what-if, sensitivity, assumption ledger
| EE-1 Data/GIS |  | Elevation, land cover and footprint data; catchment and low-lying zones; layer package; elevation-agreement check
| EE-2 Dashboard |  | Four-screen dashboard, formula implementation, advisory prototype, 3D viewer embed, demo and video
| EE-3 Evidence & Pitch |  | Survey, flood-spot back-test, responsibility map, sources and licences, business case, deck text
| Whole team |  | Shared set-up, check-ins, go/no-go gate, submission and link testing
How to use
1. Enter names in the Team table above and in the Owner column of 'Task List'.
2. Set each task's Status using the dropdown: Not started, In progress, Blocked, Done.
3. 'Summary' shows progress by role; 'Timeline' shows the Gantt view; 'Hand-offs' lists what moves between people.
4. Any new assumed number goes into 'Assumption Ledger'. Take volumes only from the Mechanical lead's table.
5. Add new tasks by inserting rows inside the table on 'Task List' (Summary covers rows 5 to 100).
Rules to protect credibility
- 3D and map visuals show risk bands or scenarios, never predicted flood depths (terrain error is about 1 m).
- Alerts are advisory and built on official warnings. Never call them a forecast.
- Use neutral wording. Show flow paths and capacity gaps, not blame.
- If behind schedule, drop in this order: stretch hydrology model, demo-video 3D visuals, bench sensor demo.
- Items marked [verify] in 'Open Items' must be confirmed before submitting.

## Task List
Task List
Edit Owner, Status and Notes. Phase is calculated from Start day. Day 1 date is set on README.
ID | Role | Workstream | Task | Deliverable | Priority | Phase | Start day | End day | Depends on | Receives from | Gives to | Owner (name) | Status | Notes
G1 | Whole team | Set-up | Set up shared folder, layer naming, units and coordinate system | One-page data contract | Core |  | 1 | 1 |  |  | All |  | Not started
G2 | Whole team | Set-up | Agree study-area boundary; label SDP land, other developers' land and council areas | Boundary map and note | Core |  | 1 | 2 |  | Public SDP maps and press | All |  | Not started
G3 | Whole team | Coordination | Daily 10-minute check-in | Notes in shared folder | Core |  | 1 | 13 |  |  | All |  | Not started
G4 | Whole team | Coordination | Go/no-go gate: layers load and catchment looks plausible | Decision recorded | Core |  | 3 | 3 | D3, D6, A1 |  | All |  | Not started
G5 | Whole team | Submission | Compile submission package: deck (max 10 main slides), 5-minute video link, prototype link, supporting docs | Complete package | Core |  | 12 | 13 | S8, W8 |  | Judges |  | Not started
G6 | Whole team | Submission | Test every link signed-out or in incognito; proofread | Checklist ticked | Core |  | 13 | 13 | G5 |  | Judges |  | Not started
D1 | EE-1 Data/GIS | Data | Download elevation models (FABDEM plus a second model for comparison); check licence terms | Raster files and licence note | Core |  | 1 | 2 | G1 |  | D3, A1 |  | Not started
D2 | EE-1 Data/GIS | Data | Download land cover, building footprints and roads | Layer files | Core |  | 1 | 2 | G1 |  | D3, A1, M2 |  | Not started
D3 | EE-1 Data/GIS | Analysis | Delineate catchment and flow paths using the Mechanical lead's parameters | Catchment polygon and flow lines | Core |  | 2 | 4 | D1, D2, M2 | Mechanical (parameters) | M1, A5 |  | Not started
D4 | EE-1 Data/GIS | Analysis | Map low-lying zones and risk bands | Risk-band layer | Core |  | 3 | 4 | D3 |  | S4, W2, A4 |  | Not started
D5 | EE-1 Data/GIS | Validation | Elevation-agreement check: which high-risk cells hold across two terrain models | Robust-hotspot layer and note | Core |  | 4 | 5 | D4 |  | W2, S8 |  | Not started
D6 | EE-1 Data/GIS | Data | Deliver clean layer package v1 (naming, units, coordinate system) | Layer package | Core |  | 2 | 3 | D1, D2, G1 |  | A1, M1, M2 |  | Not started
A8 | Architecture | 3D modelling | Visual style sheet: colours for risk bands, ownership, flow paths (accessible) | One-page style sheet | Core |  | 1 | 2 |  |  | W1, S8 |  | Not started
A1 | Architecture | 3D modelling | Base 3D site model: terrain, buildings, roads, Townpark and ponds | Model file plus GLB export | Core |  | 1 | 4 | D1, D2, D6 | EE-1 (terrain, footprints) | A2, A5, W6 |  | Not started
A2 | Architecture | 3D modelling | Parametric pond and wetland objects (area and depth adjustable); Townpark from SDP booklet; Taman Mutiara pond | Pond objects | Core |  | 3 | 5 | A1 | Mechanical (inputs) | A3, A4 |  | Not started
A3 | Architecture | Design options | Blue-green option library: deeper pond, extra pond, wetland, swale, bioretention, dual-use park | Options catalogue with area, depth, volume | Core |  | 4 | 6 | A2, M4 | Mechanical (volumes) | W3, S8 |  | Not started
A5 | Architecture | 3D modelling | Flow-path scene: Setia Alam to BBR route and council boundaries | Annotated scene | Core |  | 5 | 6 | A1, D3 | EE-1 (flow lines) | W6, S8 |  | Not started
A4 | Architecture | 3D modelling | Scenario views: existing versus added storage, with risk bands (labelled illustrative) | 3-4 rendered scenes | Core |  | 6 | 8 | A2, A3, D4 | Mechanical (storage gap) | S8, W6 |  | Not started
A6 | Architecture | 3D modelling | Optimise web assets (small files, clear layer names) | GLB files and layer list | Core |  | 6 | 8 | A1, A2 |  | W6 |  | Not started
A7 | Architecture | 3D modelling | Flythrough or storyboard for the 5-minute video | Clip or storyboard | Stretch |  | 9 | 11 | A4, A6 |  | W8 |  | Not started
M2 | Mechanical | Hydrology | Design inputs from MSMA 2: rainfall intensity for design storm, runoff coefficients, time of concentration (note outdated curves) | Parameter table with sources | Core |  | 1 | 3 | D2 |  | D3, M3 |  | Not started
M8 | Mechanical | Governance | Maintain the assumption ledger | Assumption Ledger sheet | Core |  | 1 | 13 |  | All | All |  | Not started
M1 | Mechanical | Hydrology | Review catchment: area, slope, flow paths; confirm the Setia Alam contribution is plausible | Approved catchment and note | Core |  | 3 | 4 | D3, D6 | EE-1 (catchment) | M3 |  | Not started
M3 | Mechanical | Hydrology | Compute storage required for the design storm as low, central and high values | Storage-required table | Core |  | 3 | 5 | M1, M2 |  | M4, M5, A3 |  | Not started
M4 | Mechanical | Hydrology | Pond what-if engine: volume balance for given area and depth (optionally routed) | Validated formulas and test cases | Core |  | 4 | 6 | M3 |  | W3, A3 |  | Not started
M5 | Mechanical | Hydrology | Reconcile existing storage (Townpark 16,000 / 34,000 / 50,000 m3; Taman Mutiara about 2 ha) against requirement | Storage-gap table with ranges | Core |  | 5 | 6 | M3, M4 |  | A4, S8 |  | Not started
M6 | Mechanical | Analysis | Sensitivity analysis: rainfall, runoff, pond depth, terrain error | One-page chart and table | Core |  | 7 | 8 | M5 |  | S8 |  | Not started
M7 | Mechanical | Validation | Plausibility back-test against documented floods (Dec 2021, Jun 2023, Apr 2024); report honestly, do not tune | Short note | Core |  | 7 | 8 | M5, S3 | EE-3 (flood spots) | S4, S8 |  | Not started
M9 | Mechanical | Hydrology | Stretch: simple rainfall-runoff model of the sub-catchment (e.g. HEC-HMS) | Run and notes | Stretch |  | 8 | 10 | M5 |  | S8 |  | Not started
W1 | EE-2 Dashboard | Dashboard | Dashboard skeleton and layout using the style sheet | Working shell | Core |  | 3 | 4 | A8 | Architecture (style) | W2 |  | Not started
W2 | EE-2 Dashboard | Dashboard | Screen 1: catchment map with flood-spot overlay and robust-hotspot layer | Screen 1 | Core |  | 5 | 6 | W1, D4, D5, S3 | EE-1 (layers) | W7 |  | Not started
W3 | EE-2 Dashboard | Dashboard | Screen 2: pond what-if with sliders; implement Mechanical formulas | Screen 2 | Core |  | 6 | 8 | M4, A3, W1 | Mechanical (formulas) | W7 |  | Not started
W4 | EE-2 Dashboard | Dashboard | Screen 3: responsibility panel (agency, contact, confidence label) | Screen 3 | Core |  | 6 | 7 | S5, W1 | EE-3 (template) | W8 |  | Not started
W5 | EE-2 Dashboard | Advisory | Screen 4: advisory prototype from official MET Malaysia warnings; label 'advisory, not a forecast' | Screen 4 | Core |  | 7 | 9 | W1 |  | W8 |  | Not started
W6 | EE-2 Dashboard | Dashboard | Embed the 3D viewer (GLB models) | Working 3D view | Core |  | 8 | 9 | A6, A5, A4 | Architecture (GLB) | W8 |  | Not started
W7 | EE-2 Dashboard | Validation | Verify dashboard formulas against hand calculations | Test log | Core |  | 8 | 9 | W3, M4 | Mechanical (test cases) | W8 |  | Not started
W8 | EE-2 Dashboard | Demo | Package the demo and record the 5-minute video | Video link and demo build | Core |  | 10 | 12 | W2-W7, A7 |  | G5 |  | Not started
S1 | EE-3 Evidence & Pitch | Survey | Build and launch the resident survey (English and Bahasa Malaysia; privacy line; flood and 'whom do you contact' questions) | Live survey link | Core |  | 1 | 2 |  |  | S2 |  | Not started
S3 | EE-3 Evidence & Pitch | Evidence | Compile documented flood spots: street, date, depth, source | Flood-spot table (CSV) | Core |  | 1 | 3 |  | Public press and residents | D4, M7, W2, S4 |  | Not started
S6 | EE-3 Evidence & Pitch | Governance | Maintain sources-and-licences list (data and API terms) | Sources sheet / appendix | Core |  | 1 | 13 |  | All | S8 |  | Not started
S5 | EE-3 Evidence & Pitch | Evidence | Responsibility-map template; fill only with documented facts; mark confidence | Template and entries | Core |  | 4 | 6 | S3 |  | W4 |  | Not started
S4 | EE-3 Evidence & Pitch | Validation | Back-test: share of documented flood spots flagged high-risk (hit rate, X of Y) | Hit-rate result | Core |  | 5 | 7 | D4, S3 | EE-1 (risk bands) | S8 |  | Not started
S7 | EE-3 Evidence & Pitch | Business case | Value to SDP, scale-up, cost-benefit with stated assumptions | Business-case section | Core |  | 5 | 9 |  |  | S8 |  | Not started
S9 | EE-3 Evidence & Pitch | Hardware | Optional: bench water-level sensor demo (labelled a demonstration) | Bench demo | Optional |  | 7 | 10 |  |  | W8 |  | Not started
S2 | EE-3 Evidence & Pitch | Survey | Analyse survey results (n, who responded, limits stated) | Results summary | Core |  | 8 | 9 | S1 |  | S8 |  | Not started
S8 | EE-3 Evidence & Pitch | Pitch | Deck narrative and appendix text; combine visuals, numbers and validation | Deck (max 10 main slides) and appendix | Core |  | 8 | 12 | M5, M6, S2, S4, S7, A4 | All | G5 |  | Not started

## Summary
Progress Summary
All figures are formulas driven by the Status column on 'Task List'.
Role | Lead | Not started | In progress | Blocked | Done | Total | % Done
Architecture
Mechanical
EE-1 Data/GIS
EE-2 Dashboard
EE-3 Evidence & Pitch
Whole team
Total
By priority
Priority |  | Not started | In progress | Blocked | Done | Total | % Done
Core
Stretch
Optional
Schedule
Days remaining to deadline
Project day today
Core tasks due by today and not done

## Timeline
Timeline (Gantt)
Bars follow Start and End day on 'Task List'. Teal = Core, amber = Stretch/Optional. The current project day is outlined.
[5 empty] | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ID | Role | Task | Priority | Start | End

## Hand-offs
Hand-offs
What must move between people, in what format, and by when. Delays here block other roles.
# | From | To | What | Format | Needed by (day) | Linked tasks | Received?
1 | Mechanical | EE-1 Data/GIS | Delineation parameters (thresholds, outlet point) | Short doc | 2 | M2, D3
2 | EE-1 Data/GIS | Mechanical | Catchment polygon, land cover, elevation models | GeoTIFF / GeoJSON | 3 | D3, D6, M1
3 | EE-1 Data/GIS | Architecture | Terrain, building footprints, roads | GeoTIFF / OBJ / GeoJSON | 3 | D6, A1
4 | EE-3 Evidence & Pitch | Mechanical, EE-1 | Documented flood spots with dates and sources | CSV | 3 | S3, M7, D4
5 | Mechanical | EE-2 Dashboard | Formulas, units and test cases for the what-if | Document and CSV | 5 | M4, W3
6 | Mechanical | Architecture | Storage volume for each pond option | Table | 5 | M3, A3
7 | Architecture | EE-2 Dashboard | GLB models, layer list and style sheet | GLB and one-page PDF | 6 | A6, A8, W6
8 | EE-1 Data/GIS | EE-2 Dashboard | Risk-band and robust-hotspot layers | GeoJSON | 5 | D4, D5, W2
9 | EE-3 Evidence & Pitch | EE-2 Dashboard | Responsibility-map template and entries | CSV | 6 | S5, W4
10 | Mechanical | EE-3 Evidence & Pitch | Storage gap, sensitivity chart and ledger for the deck | Table and chart | 8 | M5, M6, S8
11 | EE-3 Evidence & Pitch | All | Survey results and sources list | Summary doc | 9 | S2, S6
12 | Architecture | EE-3 Evidence & Pitch | Scenario visuals for the deck | PNG / PDF | 11 | A4, S8
13 | EE-2 Dashboard | All | Working demo build | Link | 10 | W2-W7

## Assumption Ledger
Assumption Ledger
Every number we did not measure. Owner: Mechanical lead. Replace 'Assumed' and 'Unknown' values when better data arrives.
# | Item | Value or range | Status | Source or basis | Effect if wrong | Replace with | Owner
1 | Wetland Townpark storage | 16,000 m3 normal; 34,000 m3 additional; 50,000 m3 maximum | Sourced | SDP Bandar Bukit Raja booklet (design figures, not as-built) | Over- or under-states storage | As-built data | Mechanical
2 | Taman Mutiara pond area | About 2 ha | Sourced | Selangor Journal (undated); confirm date and completion | Same | Council drawings | Mechanical
3 | Taman Mutiara pond depth and status | [TBD] m; completion unconfirmed | Unknown | Utusan Nov 2024: 25% built, delayed by pump-capacity issues | Storage mis-estimated | Council or JPS data | Mechanical
4 | Other ponds in BBR Phases 1-2 | [TBD] | Unknown | Residents described four in 2024 | Missing storage | SDP inventory | Mechanical
5 | Design storm | [TBD] mm/h for [TBD]-year event | Assumed | MSMA 2 curves (may be outdated) | Storage need under- or over-stated | Updated local rainfall data | Mechanical
6 | Runoff coefficient | [TBD] | Assumed | Land-cover table | Runoff mis-estimated | Site data | Mechanical
7 | Terrain vertical error | About 1.1 m in built-up areas | Sourced | Developer-reported for FABDEM (Fathom) | Low-lying zones misranked | LiDAR (JUPEM or SDP) | Mechanical
8 | Drain capacity and pump rates | Not modelled | Unknown | No public data | Local failures missed | Drain and pump inventory | Mechanical
9 | Catchment area (Setia Alam to BBR) | [computed] | Computed | From elevation model (D3, M1) | Contribution mis-stated | Reviewed delineation | Mechanical
10 | Storage required | [computed: low / central / high] | Computed | M3 | Gap mis-stated | Updated inputs | Mechanical

## Open Items
Open Items and Risks
Verify before submitting; manage risks every few days.
# | Type | Item | Why it matters | Owner | Status
1 | Verify | Year of the SDP managing director's 'top priority' quote (The Edge) | Used on Slide 2 | EE-3 Evidence & Pitch | Open
2 | Verify | Whether the Taman Mutiara pond was completed after March 2025; date and amount of the Selangor Journal report | Affects storage numbers and the story | Mechanical | Open
3 | Verify | Geographic scope of '300 unmanned ponds / 55 taken over by DID' (Klang or wider) | Cited on Slide 4 | EE-3 Evidence & Pitch | Open
4 | Verify | Which BBR neighbourhoods SDP actually developed (Taman Mutiara, Pekan Meru may not be SDP) | Labels on all maps and slides | Whole team | Open
5 | Verify | FABDEM licence terms for a competition submission | Legal use of data | EE-1 Data/GIS | Open
6 | Verify | data.gov.my licence and rate limits | Advisory prototype | EE-2 Dashboard | Open
7 | Verify | Whether myPublicInfoBanjir offers any permitted access (do not scrape) | Data source for alerts | EE-2 Dashboard | Open
8 | Verify | Whether the organisers set a 2-3 year implementation expectation | Slide 9 wording | Whole team | Open
9 | Verify | Read remaining SDP booklet pages (1, 2, 4, 6) for more volumes | Better starting numbers | Mechanical | Open
10 | Verify | Do not use KLASS RM144m or RM574.5m figures (appeared only in search summaries) | Unsupported claims | EE-3 Evidence & Pitch | Open
11 | Risk | Overclaiming accuracy (terrain error is about 1 m) | Credibility. Mitigation: risk bands, ledger, sensitivity chart | Mechanical | Open
12 | Risk | Sounding like we blame SDP, councils or residents | Sensitivity. Mitigation: neutral language, flow paths and capacity only | Whole team | Open
13 | Risk | Advisory mistaken for an official warning | Liability. Mitigation: label, link official source, opt-in | EE-2 Dashboard | Open
14 | Risk | Scope creep (building tier B or C) | Time. Mitigation: core tasks only; use drop order on README | Whole team | Open
15 | Risk | Saying 'nothing is being done' (many projects exist) | Credibility. Frame as separate programmes with no shared view | EE-3 Evidence & Pitch | Open
16 | Risk | Quoting the 2024 'four shallow ponds' as current | Accuracy. Say 'residents said in 2024' | EE-3 Evidence & Pitch | Open
17 | Risk | Treating SDP booklet figures as as-built | Accuracy. They are design and marketing figures | Mechanical | Open
18 | Risk | No one owns the business case | 10% of score. Assigned to EE-3 | EE-3 Evidence & Pitch | Open
19 | Risk | Large 3D files slow the web dashboard | Demo reliability. Mitigation: A6 optimisation | Architecture | Open